## Sheet1
W266 Final Project TO-DOs
Category | Tasks | People | Due Dates | Duration | Note | Class Due Dates
Data collection | List of M&A Deals | YH | 2020-05-30 | 1W
| Think about how to scrape transcripts and tagging | YH, SI, VR | 2020-05-30 | 1W | https://seekingalpha.com/earnings/earnings-call-transcripts if you need to log in: yinghua26@gmail.com, 198eight.
Literature review | Review main literatures | YH, SI, VR | 2020-05-30 | 1W
Instructor catch up | Walk SID through the project | YH, SI, VR | 2020-05-30 | 1W
Proposal |  |  | 2020-06-07 |  |  | Project proposal
Data collection | Scraping transcripts | YH, SI, VR | 2020-06-14 | 2W
Ananlysis | EDA | YH, SI, VR | 2020-06-21 | 1W
| Baseline model | YH, SI, VR | 2020-06-28 | 1W
| Trying different models | YH, SI, VR | 2020-07-05 | 1W
Write up | Milestone report | YH, SI, VR | 2020-07-12 | 1W |  | *Optional: check in with instructor
Modifications | Data, model | YH, SI, VR | 2020-07-26 | 2W
| Final Report | YH, SI, VR | 2020-08-01 | 1W |  | Final report deadline
| Final Presentation | YH, SI, VR | 8/3 - 8/7 |  |  | Final Presentation due